## Slide 1
Superfeet.com
Assessment & Acceleration Plan
Arcadia Digital | February 2024

## Slide 2: Roadmap & Investments

## Slide 3: Current Roadmap Review
The acceleration plan alter the timing and sequencing of the current roadmap. Some items are OK to keep as-is.
Many items will either be addressed as part of re-platforming to Shopify or can be pulled forward.
Current Timeline | Initiative | JTP Comments | New Timeline
2024 | Tie GA4 with Magento and Power BI for more accurate reporting. Connected to Datacube | OK to keep - but align with updated GA4 implementation with Shopify replatform phase 1 | 2024
2024 | Leverage PowerBI to predict churn and identify consumers to retain | Ok to keep since this is isolated to BI | 2024
2024 | Explore feasibility of bundles and subscriptions cross-functionally (US). Deploy bundles and subscriptions (US) | Explore feasibility but plan to execute as part of Shopify replatforming phase 1 or phase 2 | 2024
2024 | Expand alternative payment methods to other regions: Amazon Pay, BNPL/Klarna/Affirm | Execute as part of Shopify replatforming Phase 1 or 2 | 2024
2024 | Improve post-purchase consumer experience with ship tracking service provider (US) | Execute as part of Shopify replatforming Phase 2. Explore popular Shopify apps such as AfterShip, Narvar, Loop, etc. | 2024
2024 | Prepare and structure site and product data for AI personal shopping – all regions | Depends on specific tool selected. Delay this and consider how SearchSpring helps accomplish this goal or not as part of Shopify implementation. Explore Shopify friendly apps/native solutions as part of Replatforming phase 2 | 2024
2024 | Expand US chat to include insole finder-like product recommendations | OK to keep - this is operational, not tech stack related. | 2024
2024 | Launch V2 Insole Finder | Ok to keep - but align timing with Shopify replatform design phase so the front end experience with Cartful is aligned. | 2024
2024 | Launch SMS in US | Ok to keep but consider timing and rollout and explore Klaviyo as a potential vendor if also migrating CRM/Email tool | 2024
2024 | Update store locator for Med+ | Ok to keep - largely unrelated to DTC roadmap | 2024
2024 | Blog added to Superfeet Rx | Ok to keep but line up with Shopify replatform Phase 1 or 2 | 2024
2024 | Test and learn for Work bulk orders | Need more information. Is this related to quantity discounts? Ok to keep if yes, but design the program using Shopify capabilities out of the box | 2024
2025 | Begin Platform Migration, Platform selection, Vendor Selection, Site Architecture | Pull up to 2024 | 2024
2025 | Launch new ecommerce platform Q4 | Pull up to 2024 | 2024
2025 | Identify and select emerging AI services to improve and streamline consumers’ online shopping experience | This is vague. Ok to keep as a 2025 initiative and explore Shopify apps/add-ons to support as the business strategy is further refined | 2025
2025 | Prepare multi-language AI integration with new ecomm platform: French/French for Canada, German | Should be considered in conjunction with line item above | 2025
2025 | Expand bundles and subscriptions to appropriate regions | Pull forward to back half of 2024 with Shopify platform phase 2 | 2024
2025 | Add post-purchase shipment tracking to appropriate regions | Ok to keep | 2025
2025 | Work with IT to expand Chat to new regions | Ok to keep | 2025
2025 | Collaborate with content team and conversion specialist to develop content personalization pilot program (US) for dynamic on-site shopping experiences | Ok to keep | 2025
2025 | Launch SMS in appropriate regions | Ok to keep | 2026
2026 | Expand DtC: Quebec, Germany, Investigate and prepare for expansion in EMEA & LATAM | Ok to keep. Could potentially pull into 2025 depending on business strategy. | 2026
2026 | Leverage emerging AI services for: Improved personalization, Smart pricing and promotion, Enhanced product recommendation, Consumer Retention and Loyalty | Pull up into 2025. Shopify will make this easier to deploy from a technical standpoint. | 2025
2026 | Expand content personalization program to additional regions, Prioritize regions for expansion | Ok to keep or potentially pull into 2025 | 2026
2026 | Expand multi-language to add selected regions: EMEA, LATAM | Ok to keep | 2026
2026 | Investigate same-day delivery (US) (if not already a thing) | Ok to keep. Would pull into 2025 | 2025
Address with Shopify Phase 1 or 2
Pulling forward is possible

## Slide 4: 18 Month Roadmap and Workstreams
36
An estimated 3 Year pro forma shows a path to profitable revenue growth using a different approach with franchise partners
Note: Estimated Timeline - To be validated during full discovery.
 | March 2024: Kickoff | Q2-24 | Q3-24 | Q4-24 | Q1-25 | Q2-25 | Q3-25
General Business, Planning & Strategy, Operational Excellence | Discovery & Plann | ing Ongoing strateg | ic digital and Operatin | g Model, Process, and Ca | pability Development (V | alue Creation Priority Ac | tions)
Re-platform Phase 1: Migrate & Improve | Discovery & Plann | ing Launch on Sh | opify Plus |  | Brand Refresh |  | 
Re-platform Phase 2: Expand & Accelerate | Discovery & Plann | ing |  | Shopify Plu | s Feature Expansion |  | 
Digital Lifecycle Marketing | Discovery & Plann | ing Phase 1: Launch | & Quick Wins | Phas | e 2: Scaled Acquisition | & Retention | 
Data, Analytics, Insights, Financial Linkages | Discovery & Plann | ing Integration with | new Shopify In | tegration with Scaled D | igital Lifecyle Marketing | Program | 
New Business Model Development |  |  |  | Subscription, Guided Sh | opping, Custom Produ | ct, Bundles, etc. | 
Transition & Stabilize |  |  |  |  | Onboar | d and transfer to Stabili | zed Team